WBS( Work Breakdown Structure)

| No. | Activity/Task |  | Milestone/ Deliverable | Duration (hrs) | Duration (days) | Precedence | Sujina | Pasang | Manav |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 Planning |  |  |  |  |  |  |  |  |  |
| 1.1 | Determine Project Title |  |  | 0.5 | 1 | NIL | 100 | 100 | 100 |
| 1.2 | Write the Overview |  |  | 1 | 1 | 1.1 | 100 | 0 | . |
| 1.3 | Write the Aims & Objectives |  |  | 2 | 1 | 1.1 | 0 | 100 | 0 |
| 1.4 | Write the Scope |  |  | 2 | 1 | 1.1 | 0 | 0 | 100 |
| 1.5 | Derive WBS |  |  | 8 | 1 | 1.4 | 100 | 100 | 100 |
| 1.6 | Determine Milestones |  |  | 2 | 1 | 1.5 | 100 | 100 | 100 |
| 1.7 | Derive Gantt Chart |  |  | 8 | 1 | 1.7 | 100 | 100 | 100 |
| 1.8 | Derive Technical Platform |  |  | 3 | 1 | 1.7 | 100 | 0 | 0 |
| 1.9 | Derive Risk Management Plan |  |  | 3 | 1 | 1.7 | 0 | 100 | 100 |
| 1.10 | Project Plan/Proposal |  | Milestone/Deliverable |  |  | 1.8,1.9 | 100 | 100 | 100 |
| 2 Requirements |  |  |  |  |  |  |  |  |  |
| 2.1 | Determine Functional & Non-Functional Requirements |  |  | 8 | 2 | 1.9 | 100 | 100 | 100 |
| 2.2 | Modeling Requirements (User Stories, AC, Tasks) |  |  |  |  | 2.1 |  |  |  |
| 2.2.1 | UC1-User Registration & Privacy Settings |  |  | 8 | 2 | 2.1 | 100 | 0 | 0 |
| 2.2.2 | UC2-Manage Food Inventory |  |  | 8 | 2 | 2.1 | 0 | 100 | 0 |
| 2.2.3 | UC3 - Browse Food Items & Donations |  |  | 8 | 2 | 2.1 | 0 | 0 | 100 |
| 2.2.4 | UC4 - Food Analytics |  |  | 8 | 2 | 2.1 | 100 | 0 | 0 |
| 2.2.5 | UC5 – View Notifications |  |  | 8 | 2 | 2.1 | 0 | 100 | 0 |
| 2.2.6 | UC6 – Plan Weekly Meals |  |  | 8 | 2 | 2.1 | 0 | 0 | 100 |
|  | Requirements Specifications Document (docx) |  | Milestone/Deliverable |  |  | 2.2.6 | 100 | 100 | 100 |
| 3 Design |  |  |  |  |  |  |  |  |  |
| 3.1 |  | Design UX / Wireframes |  |  |  | 2.3 |  |  |  |
| 3.1.1 |  | Wireframes UC1 – User Registration |  | 4 | 1 | 2.3 | 50 | 0 | 0 |
| 3.1.2 |  | Wireframe UC2 – Food Inventory |  | 4 | 1 | 2.3 | 0 | 50 | 0 |
| 3.1.3 |  | Wireframe UC3 – Browse Donations |  | 4 | 1 | 2.3 | 0 | 0 | 50 |
| 3.1.4 |  | Wireframe UC4 – Analytics Dashboard |  | 4 | 1 | 2.3 | 50 | 0 | 0 |
| 3.1.5 |  | Wireframe UC5 – Notifications |  | 4 | 1 | 2.3 | 0 | 50 | 0 |
| 3.1.6 |  | Wireframe UC6 – Meal Planner |  | 4 | 1 | 2.3 | 0 | 0 | 50 |
| 3.2 |  | Design Site Map (Hierarchy Diagram) |  | 4 | 1 | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6 | 100 | 100 | 100 |
| 3.3.1 |  | Design ERD |  | 4 | 1 | 2.3 | 100 | 0 | 0 |
| 3.3.2 |  | Design Data Dictionary |  | 4 | 1 | 3.3.1 | 0 | 100 | 100 |
| 3.4 |  | Architectural/Deployment Diagram |  | 4 | 1 | 3.3.2 | 100 | 100 | 100 |
| 3.5 |  | Design Specification Document | Milestone/Deliverable |  |  | 3.4 | 100 | 100 | 100 |
| 4 Iteration 1 – Core Features |  |  |  |  |  |  |  |  |  |
| 4.1 |  | Code & Test UC1: User Registration & Privacy |  | 40 | 5 | NIL | 100 | 0 | 0 |
| 4.1.1 |  | Working UC1 Feature | Milestone |  |  | 4.1 | 100 | 0 | 0 |
| 4.2 |  | Code & Test UC2: Manage Food Inventory |  | 56 | 7 | 4.1.1 | 0 | 100 | 0 |
| 4.2.1 |  | Working UC2 Feature | Milestone |  |  | 4.2 | 0 | 100 | 0 |
| 4.3 |  | Code & Test UC3: Browse Food Items & Donations |  | 40 | 5 | 4.2.1 | 0 | 0 | 100 |
| 4.3.1 |  | Working UC3 Feature | Milestone |  |  | 4.3 | 0 | 0 | 100 |
| 4.4 |  | Integration Testing – Iteration 1 |  | 16 | 2 | 4.3.1 | 100 | 100 | 100 |
| 4.5 |  | Iteration 1 Prototype | Milestone/Deliverable |  |  | 4..4 | 100 | 100 | 100 |
| 5 Iteration 2 – Advanced Features |  |  |  |  |  |  |  |  |  |
| 5.1 |  | Code & Test UC4: Food Analytics |  | 32 | 4 | 4.5 | 100 | 0 | 0 |
| 5.1.1 |  | Working UC4 Feature | Milestone |  |  | 5.1 | 100 | 0 | 0 |
| 5.2 |  | Code & Test UC5: View Notifications |  | 32 | 4 | 5.1.1 | 0 | 100 | 0 |
| 5.2.1 |  | Working UC5 Feature | Milestone |  |  | 5.2 | 0 | 100 | 0 |
| 5.3 |  | Code & Test UC6: Plan Weekly Meals |  | 32 | 4 | 5.2.1 | 0 | 0 | 100 |
| 5.3.1 |  | Working UC6 feature | Milestone |  |  | 5.3 | 0 | 0 | 100 |
| 5.4 |  | Integration Testing – Iteration 2 |  | 16 | 2 | 5.3.1 | 100 | 100 | 100 |
| 5.5 |  | User Acceptance Testing (UAT) |  | 24 | 3 | 5.4 | 100 | 100 | 100 |
| 5.6 |  | Bug Fixing & Regression Testing |  | 16 | 2 | 5.5 | 100 | 100 | 100 |
| 5.7 |  | Performance & Security |  | 8 | 1 | 5.7 | 100 | 0 | 0 |
| 5.8 |  | Final System :Assignment 2 Submission | Milestone/Deliverable |  |  | 5.8 | 100 | 100 | 100 |