Table of Contents

1.0 Initiating Task	1

1.1 Business Case	1

1.2 Three Sphere Model	4

1.3 Project Charter	11

2.0 Planning Tasks	14

2.1 Scope Statement	14

2.2 Work Breakdown Structure(WBS)	16

2.3 Work Items List	17

2.4 Cost Estimate	19

2.5 Communications Management Plan	22

2.6 Quality Management Plan	23

2.7 Risk Management Plan	25

2.8 Stakeholder Management Strategy	28

GitHub Link	28

Reference	28

# 1.0 Initiating Task

## 1.1 Business Case

Project Name: SmartPantry

| Section | Details |
| --- | --- |
| 1.0 Introduction/ Background | Malaysia is one of the highest per capita food waste producers in Southeast Asia, with waste production of about 16,688 tons per day. Household food waste is a major contributor, that is often caused by poor inventory tracking and lack of awareness about expiry dates. |
| 2.0 Business Objective | - Track and manage their food inventory with monitoring of expiry date - Receive timely notifications before food items expire - Browse and claim food donation - Plan weekly meals based on available inventory - View food analytics and track their environmental impact |
| 3.0 Current Situation and Problem/Opportunity Statement | Currently, there is no household food waste management app that is widely used in Malaysia. The existing platform focus on commercial food redistribution rather than household inventory management. The opportunity exists to fill this gap with a web application that is specifically designed for Malaysian households. The growing awareness of food waste as an issue creates a strong market opportunity for SmartPantry |
| 4.0 Critical Assumptions and Constraints | Assumptions: - Team members have knowledge in Django, React and PostgreSQL - Internet Connectivity is stable - Personal laptops provide sufficient hardware resources for development - Case study requirements remain unchanged throughout the project Constraints: - 14 week academic timeline - Three person development team - Fixed assignment submission deadlines - Estimated budget of RM 92,000 for real world deployment scenario |
| 5.0 Analysis of Options and Recommendations | Option 1: Do Nothing Option 2: Use existing platform Option 3: Develop SmartPantry Recommendation: Develop a custom web application covering all 6 use cases |
| 6.0 Preliminary Project Requirements | - UC1: User Registration and Privacy Settings with 2FA, email verification and privacy controls - UC2: Manage food inventory with add, edit, delete items option and expiry tracking - UC3: Browse Food Items and Donations with filter, claim and post donation listings - UC4: Food Analytics Dashboard with visual charts, date range filters - UC5: View Notifications with expiry alerts, donation updates and meal reminders - UC6: Plan Weekly Meals with calendar view, meal suggestions Technology Stack: React.js for frontend, Django for backend, PostgreSQL for database and websocket for notifications |
| 7.0 Budget estimate and Financial Analysis | Cost Assumptions (3 Year Business case): - Development labor (908 hrs @RM 80 per hour): RM 72,640 - UI/UX Design (Figma): 5,000 - Cloud Hosting (Year 1): RM 6,000 - Reserves (10%): RM 8,360 - Total Initial Investment (Year 0): RM 92,000 Revenue Assumptions: Year 1: Freemium model launch, grant funding (RM 25,000 net benefit) Year 2 : Premium subscriptions(RM 50,000 net benefit) Year 3: In app advertising and scaled user based RM 75,000 net benefit) 3 Year Financial Analysis (with Discount Rate: 8%) Year; Net Benefit (RM); Discount Factor (8%); Present Value (RM). 0(Initial Investment); (92,000); 1.00; (92,000). 1; 25,000; 0.926; 23,148. 2; 50,000; 0.857; 42,867. 3; 75,000; 0.794; 59,537. Total PV of benefits; 150,000; 125,552. NPV = RM 125,552 – RM 92,000 = RM 33,552 (Positive – project is financially viable) ROI = (125,552 – 92,000) / 92,000 * 100 = 36.5% Payback period approx 2.3 years (Year 1 recovers RM 25,000, Year 2 recovers RM 50,000, remaining RM 17,000 recovered early year 3) |
| 8.0 Schedule estimate | Milestone; Target Date. Assignment 1 Submitted; 27/06/2026. Iteration 1 Completion; 18/07/2026. Iteration 2 Completion; 04/08/2026. Assignment 2 Submitted; 21/08/2026. |
| 9.0 Potential Risks | - Low user usage during launch phase - Data privacy breach - Scope Creep due to additional feature requests - Team member availability due to academic workload |
| 10.0 Exhibits | Exhibit A: Financial Analysis Excel Sheet containing the financial analysis is uploaded in HLMS It contains full 3 year discounted cost and benefit analysis at 8% discount rate with NPV, ROI and payback period calculation and chart |

## 1.2 Three Sphere Model

The three sphere model analyses business, organizational and technological issues that is relevant to the SmartPantry project.

| Sphere | Member | Issue | Cause | How to handle/ Solution |
| --- | --- | --- | --- | --- |
| Business | Sujina Tuladhar (E2300582) | Lack of Sustainable Revenue Model |  |  |
|  |  | Low Market Awareness | Food waste reduction apps are not widely used in Malaysia due to which users are unaware of the problem and solutions | Handle: Conduct targeted social media campaigns and partner with community organizations. Solutions: Collaborate with schools, NGOs for awareness programs and app promotion |
|  | Pasang Lama (E2400050) | Competition from existing platforms | Platforms such as food banks already address some aspects of food waste redistribution. | Handle: Differentiate SmartPantry by focusing on household inventory management rather than commercial food redistribution. Solution: Identify unique selling points like expiry alerts and market them during launch. |
|  |  | Dependency on User Generated Content | SmartPantry’s donation feature relies on users actively posting food listings so low engagement reduces value | Handle: Implement elements such as badges and milestones to encourage regular app usage. Solution: Introduce a community leaderboard for food saved and donations made to make user participation |
|  | Manav Rawal (E2300560) | Legal and Compliance Requirements | App must comply with Malaysia’s Personal Data Protection Act PDPA 2010) for handing user data | Hande: Apply PDPA principles during design and implement explicit user consent and data minimization Solution: Conduct a review before deployment and include privacy policy |
|  |  | Monetization VS Social Mission Conflict | Charging users for a food waste app may discourage adoption among lower income households. | Handle: keep the core inventory tracking and donation features free and charge only for premium |
| Organizational | Sujina Tuladhar (E2300582) | 3 person Team Coordination | The team must divide work across 6 use cases and PM documentation within the academic timeline | Handle: Define clear role distribution with each member owning 2 cases and specific PM documents Solution: Use GitHub for task tracking and communicate through WhatsApp |
|  |  | Workload Imbalance Risk | PM documentation and development tasks may not be evenly distributed across all 3 members | Handle: Review task allocation weekly and redistribute if any member is overallocated Solution: Maintain a shared task tracker on GitHub projects |
|  | Pasang Lama (E2400050) | Communication and Coordination Gaps | Without a dedicated PM tool, tasks may be missed or duplicated between team members | Handle: USE GitHub for task tracking and WhatsApp for Quick Updates Solution: Establish a shared GitHub Repository |
|  |  | Stakeholder Engagement Difficulty | Lecturer feedback sessions and peer reviews may be limited within the academic term | Handle: Schedule structured feedback Solution: Document all lecturer feedback |
|  | Manav Rawal (E2300560) | Knowledge and Skill Gaps | Team members may lack experience in specific technologies such as Django, PostgreSQL and React | Handle: Identify skill gaps early and allocate time for self learning with the help of tutorials Solution: Use well documented frameworks with strong community |
|  |  | Scope Creep Due to Feature Requests | Team members may propose additional features beyond the actual 6 use cases during the development process | Handle: Strictly follow the scope defined in the Scope statement Solution: Hold weekly scope review meetings and refer to WBS and case study before adding any new feature |
| Technology | Sujina Tuladhar (E2300582) | Cross Platform Compatibility | The app must run consistently across desktop browsers with different screen sizes | Handle: Use react.js for a responsive single page application that adapts to all screen sizes Solution: Implement responsive design testing using Chrome DevTools across multiple browser viewports |
|  |  | Data Security and Privacy | User food inventory and personal data are sensitive so inadequate security could expose users to breaches. | Handle: Implement HTTPS, password hashing and role based access control from the design phase. Solution: Use Django’s built in authentication security features |
|  | Pasang Lama (E2400050) | Scalability of Local Development | Running on local host limits real world scalability demonstration during assessment | Handle: Document AWS EC2 free tier as the planned production deployment path Solution: Design the Django REST API so it can scale horizontally in future cloud deployment |
|  |  | Django, React Integration Complexity | Connecting a Django backend REST API to a react frontend requires CORS configuration and token based authentication | Handle: Insta and configure Django crs headers and use JWT tokens for secure API authentication Solution: Follow Django REST Framework documentation for token authentication and test all API endpoints with Postman before connecting React |
|  | Manav Rawal (E2300560) | Real time notification integration | Implementing real push notifications requires paid services such as Firebase which requires billing setup | Handle: Use Django channels with web socket for free Solution: Build a fallback database stored notification system that works without any external paid service |
|  |  | Database Design Complexity | SmartPantry requires multiple related tables like user, FoodItem, etc which must be correctly linked with foreign keys | Handle: Design the full ERD and data dictionary before writing any code to avoid restructuring mid development Solution: Use pgAdmin to visually manage the PostgreSQL schema |

## 1.3 Project Charter

Project Charter

| Project Title: Smart Pantry – Smart Food Waste Reduction App |  |  |  |
| --- | --- | --- | --- |
| Project Start Date: 18th May 2026 Projected Finish Date: 21st August 2026 |  |  |  |
| Budget Information: RM 92,000 estimated ( includes development labor RM 72,640, UI/UX design RM 5,000, cloud hosting RM 6,000, reserves RM8,360) |  |  |  |
| Project Manager: Sujina Tuladhar, 9767485855, sujina.tuladhar23@midvalley.edu.np |  |  |  |
| Project Objectives: - Developing fully functional Web Application covering all 6 uses by 21 August 2026. - Implement the UC1 (User Registration), UC2 (Food Inventory), UC3 (Browse Donations), UC4 (Food Analytics), UC5 (Notifications), and UC6 (Meal Planner). - Complete all the PM documentation on time. Submit Assignment 1 (due 10 July 2026) and Assignment 2 (due 21 August 2026) without any delay. - Achieve system performance of page load time under 3 seconds during local demonstration. - Let at least 10 people test the app before submitting the assignment. The app should get a SUS score higher than 70 out of 100 in the UAT (User Acceptance Test) - Complete both Black Box Testing and White Box Testing (pytest) before doing the final submission of the assignment. |  |  |  |
| Success Criteria: - All 6 Use Cases should be fully implemented and demonstrated successfully. - All PM documents should be submitted on time without missing any sections. - UAT should pass with at least a score of 70 or 100 from the test of user. - Black box testing and White Box testing should be completed with results documented. - The financial analysis shows a positive Net Present Value of RM 33,552, which means the project is expected to make a profit. - All 3 members committed their task regularly in GitHub repository. - No critical security was found during manual security review. |  |  |  |
| Approach: Smart Pantry will be developed using Iterative and Incremental methodology which has been divided into 2 iterations: - Iteration 1 (UC1-UC3): Week 8-10 (13 July- 25 July 2026) – Core features: User Registration, Food Inventory Management, Browse and Claim Donations. - Iteration 2 (UC4-UC6): Week 11-12 (27 July – 7 August 2026) – Advance Features Food Analytics, Notification’s, Weekly Meal Planner Technology Stack: - Frontend: React.js - Backend: Python + Django REST Framework - Database: PostgreSQL - Notifications: Django Channels + WebSocket - Testing: Whitebox testing (pytest) + Blackbox testing (Selenium) - Version Control: GitHub - Project Management: Gantt Project Communication: We do Weekly Team meetings through Google Meet/WhatsApp. We are using GitHub for daily task tracking of the team and code collaboration. |  |  |  |
| Roles and Responsibilities |  |  |  |
| Name and Signature | Role | Position | Contact Information |
| Sujina Tuladhar | Project Manager/ Developer | Team Leader : UC1 & UC4 | sujina.tuladhar23@midvalley.edu.np |
| Pasang Lama | Developer / Tester | Team Member : UC2 & UC5 | pasang.lama23@midvalley.edu.np |
| Manav Rawal | Developer / Tester | Team Member : UC3 & UC6 | manav.rawal23@midalley.edu.np |
| Seetha Letchumi/ Ashish Gautam / Sudeep Lal Bajimata | Supervisor / Evaluator | Lecturer : BIT301 |  |
| Comments: This project charter has been reviewed and agreed with by all the 3 members of the team. Any changes to the project scope, timeline, or budget must be formally approved by all the team members and the supervising lecturer before implementation. |  |  |  |

# 2.0 Planning Tasks

## 2.1 Scope Statement

Project Title: Smart Pantry- Smart Food Waste Reduction App Date:10/06/2026 Prepared by: Sujina Tuladhar, Pasang Lama, Manav Rawal

Project Justification: Food waste is one of the biggest issues in Malaysia. Many people throw away their food because they forget about expiry dates, don’t check the expiry date or buy more than they need. So, to reduce these things Smart Pantry is there to help users to reduce food waste by allowing them to manage their food inventory, receive daily reminder about expiry date, and donate extra food to others.

Product Characteristics and Requirements: - User Registration and Privacy Settings: Users can create an account, verify their email, enable 2FA (Two Factor Authentication) and manage their privacy settings. - Food Inventory Management: Users can add, edit and delete the food items. Items include details such as the name of food, how much quantity they are donating, what’s the expiry date of the food, and category of the food. - Donation Listing and Browsing: Users can browse the available donated food, see which food has been claimed, view pickup locations and details. - Food Analytics Dashboard: Users can view charts showing the amount of food that has been saved, number of donations that have been made, and weekly food waste trends. - Notifications: If any food is going to be expired then the system will send a notification to app or email, also if any donations have been made then the notification will appear and planning of meal reminder will also be there. - Weekly Meal Planner: The system will suggest meals based on the available food in the user’s inventory and its expiry dates.

Product User Acceptance Criteria: The product will be accepted if: - All 6 planned use cases are fully implemented. - Users can register, manage their food inventory, donate food, and receive notifications without errors. - The analytics dashboard displays accurate information. - The meal planner provides suggestions based on available food items. - The system passes UAT (User Acceptance Testing).

Summary of Project Deliverables Project management-related deliverables: - Business Case - Project Charter - Scope Statement - Work Breakdown Structure(WBS) - Work Items List - Cost Estimate - Communication Plan - Quality Plan - Risk Register - Stakeholder Management Strategy - Final Project Report - Project Presentation - Lessons Learned Report Product related deliverables: research reports, design documents, software code, hardware, etc. - System Design Document - Database Schema - Functional Web Application Prototype - UAT(User Acceptance Test) Report

## 2.2 Work Breakdown Structure(WBS)

| WBS ID | Deliverable |
| --- | --- |
| 1. | Initiating |
| 1.1 | Business Case |
| 1.2 | Three Sphere Model |
| 1.3 | Project Charter |
| 2. | Planning |
| 2.1 | Scope Statement |
| 2.2 | Work Breakdown Structure (WBS) |
| 2.3 | Work Items List |
| 2.4 | Cost Estimate |
| 2.5 | Communications Management Plan |
| 2.6 | Quality Management Plan |
| 2.7 | Risk Management Plan |
| 2.8 | Stakeholder Management |
| 2.9 | Review and Finalize Panning Documents |
| 3. | Analysis and Design |
| 3.1 | Requirements Gathering |
| 3.2 | System Architecture Design |
| 3.3 | Database Scheme Design |
| 3.4 | UI/UX Wireframes (Figma) |
| 4. | Development- Iteration 1 |
| 4.1 | UC1 User Registration and Privacy |
| 4.2 | UC2 Food Inventory Management |
| 4.3 | UC3 Browse and Claim Donations |
| 5. | Development – Iteration 2 |
| 5.1 | UC4 Food Analytics Dashboard |
| 5.2 | UC5 Notifications System |
| 5.3 | UC6 Weekly Meal Planner |
| 6. | Testing |
| 6.1 | White Box Testing (pytest) |
| 6.2 | Black Box Testing(Selenium) |
| 6.3 | User Acceptance Testing(UAT) |
| 6.4 | Bug Fixing |
| 7. | Deployment |
| 7.1 | Local Environment Setup |
| 7.2 | Application Demo Preparation |

## 2.3 Work Items List

| WBS ID | Work Item/Task | Start Date | End Date | Responsible Member |
| --- | --- | --- | --- | --- |
| Initiating |  |  |  |  |
| 1.1 | Business Case | 18/05/2026 | 23/05/2026 | Sujina Tuladhar |
| 1.2 | Three Sphere Model | 24/05/2026 | 29/05/2026 | All members |
| 1.3 | Project Charter | 30/05/2026 | 03/06/2026 | Manav Rawal |
| Planning |  |  |  |  |
| 2.1 | Scope Statement | 04/06/2026 | 06/06/2026 | Pasang Lama |
| 2.2 | WBS | 07/06/2026 | 08/06/2026 | All Members |
| 2.3 | Work Item List | 09/06/2026 | 11/06/2026 | Sujina Tuladhar |
| 2.4 | Cost Estimate | 12/06/2026 | 14/06/2026 | All Members |
| 2.5 | Communications Management Plan | 15/06/2026 | 16/06/2026 | Pasang Lama |
| 2.6 | Quality Management Plan | 17/06/2026 | 19/06/2026 | Sujina Tuladhar |
| 2.7 | Risk Management Plan | 20/06/2026 | 23/06/2026 | Manav Rawal |
| 2.8 | Stakeholder Management Strategy | 24/06/2026 | 25/06/2026 | Pasang Lama |
| 2.9 | Review and Finalize Planning Documents | 26/06/2026 | 26/06/2026 | All Members |
| Analysis and Design |  |  |  |  |
| 3.1 | Requirements Gathering | 27/06/2026 | 27/06/2026 | All Members |
| 3.2 | System Architecture Design | 28/06/2026 | 28/06/2026 | Sujina Tuladhar |
| 3.3 | Database Scheme design | 29/06/2026 | 30/06/2026 | Pasang Lama and Manav Rawal |
| 3.4 | UI/UX Wireframe | 01/07/2026 | 02/07/2026 | All Members |
| Development - Iteration 1 |  |  |  |  |
| 4.1 | UC1: User Registration and Privacy | 03/07/2026 | 17/07/2026 | Sujina Tuladhar |
| 4.2 | UC2: Food Inventory Management | 03/07/2026 | 17/07/2026 | Pasang Lama |
| 4.3 | UC3: Browse and Claim Donations | 03/07/2026 | 17/07/2026 | Manav Rawal |
| Development- Iteration 2 |  |  |  |  |
| 5.1 | UC4: Food Analytics Dashboard | 18/07/2026 | 03/08/2026 | Sujina Tuladhar |
| 5.2 | UC5: Notifications System | 18/07/2026 | 03/08/2026 | Pasang Lama |
| 5.3 | UC6: Weekly Planner | 18/07/2026 | 03/08/2026 | Manav Rawal |
| Testing |  |  |  |  |
| 6.1 | White Box testing (pytest) | 04/08/2026 | 08/08/2026 | All Members |
| 6.2 | Black Box Testing(Selenium) | 09/08/2026 | 11/08/2026 | All Members |
| 6.3 | User Acceptance Testing(UAT) | 12/08/2026 | 13/08/2026 | All Members |
| 6.4 | Bug Fixing | 14/08/2026 | 18/08/2026 | All Members |
| Deployment |  |  |  |  |
| 7.1 | Local Environment Setup | 19/08/2026 | 19/05/2026 | Sujina Tuladhar |
| 7.2 | Application Demonstration Preparation | 20/08/2026 | 20/08/2026 | All Members |

## 2.4 Cost Estimate

| WBS ID | Work Item / Task | Internal | RM/ hour | Internal | External | External | Total | Non-labor | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Labor (hrs) |  | RM Total | Labor (hrs) | RM Total | Labor RM | RM | Cost RM |
| 1 | Initiating |  |  |  |  |  |  |  |  |
| 1.1 | Business Case | 34 | 80 | 2720 | 0 | 0 | 2720 |  | 2720 |
| 1.2 | Three Sphere Model | 34 | 80 | 2720 | 0 | 0 | 2720 |  | 2720 |
| 1.3 | Project Charter | 29 | 80 | 2320 | 0 | 0 | 2320 |  | 2320 |
| 2 | Planning |  |  |  |  |  |  |  |  |
| 2.1 | Scope Statement | 17 | 80 | 1360 | 0 | 0 | 1360 |  | 1360 |
| 2.2 | WorkBreakdown Structure (WBS) | 11 | 80 | 880 | 0 | 0 | 880 |  | 880 |
| 2.3 | Work Item List | 17 | 80 | 1360 | 0 | 0 | 1360 |  | 1360 |
| 2.4 | Cost Estimate | 17 | 80 | 1360 | 0 | 0 | 1360 |  | 1360 |
| 2.5 | Communication Management Plan | 11 | 80 | 880 | 0 | 0 | 880 |  | 880 |
| 2.6 | Quality Management Plan | 17 | 80 | 1360 | 0 | 0 | 1360 |  | 1360 |
| 2.7 | Risk Management Plan | 23 | 80 | 1840 | 0 | 0 | 1840 |  | 1840 |
| 2.8 | Stakeholder Management | 11 | 80 | 880 | 0 | 0 | 880 |  | 880 |
| 2.9 | Review and Finalize Document | 6 | 80 | 480 | 0 | 0 | 480 |  | 480 |
| 3 | Executing |  |  |  |  |  |  |  |  |
| 3.1 | Analysis and Design |  |  |  |  | 0 |  |  |  |
| 3.1.1 | Requirements Gathering | 6 | 80 | 480 | 0 | 0 | 480 |  | 480 |
| 3.1.2 | System Architecture Design | 6 | 80 | 480 | 0 | 0 | 480 |  | 480 |
| 3.1.3 | Database Scheme design | 11 | 80 | 880 | 0 | 0 | 880 |  | 880 |
| 3.1.4 | UI/UX Wireframes (Figma) | 11 | 80 | 880 | 0 | 0 | 880 | 5000 | 5880 |
| 3.2 | Development - Iteration 1 |  |  |  |  |  |  |  |  |
| 3.2.1 | UC1 User Registration and Privacy | 86 | 80 | 6880 | 0 | 0 | 6880 |  | 6880 |
| 3.2.2 | UC2 Food Inventory Management | 86 | 80 | 6880 | 0 | 0 | 6880 |  | 6880 |
| 3.3.3 | UC3 Browse and Claim Donations | 86 | 80 | 6880 | 0 | 0 | 6880 |  | 6880 |
| 3.3 | Development - Iteration 2 |  |  |  |  |  |  |  |  |
| 3.3.1 | UC4 Food Analytics Dashboard | 97 | 80 | 7760 | 0 | 0 | 7760 |  | 7760 |
| 3.3.2 | UC5 Notifications System | 97 | 80 | 7760 | 0 | 0 | 7760 |  | 7760 |
| 3.3.3 | UC6 Weekly Meal Planner | 97 | 80 | 7760 | 0 | 0 | 7760 |  | 7760 |
| 3.4 | Testing |  |  |  |  |  |  |  |  |
| 3.4.1 | White Box Testing (pytest) | 29 | 80 | 2320 | 0 | 0 | 2320 |  | 2320 |
| 3.4.2 | Black Box Testing (Selenium) | 17 | 80 | 1360 | 0 | 0 | 1360 |  | 1360 |
| 3.4.3 | User Acceptance Testing (UAT) | 11 | 80 | 880 | 0 | 0 | 880 |  | 880 |
| 3.4.4 | Bug Fixing | 29 | 80 | 2320 | 0 | 0 | 2320 |  | 2320 |
| 4 | Monitoring and Controlling |  |  |  |  |  |  |  |  |
| 4.1 | Application Demonstration Preparation | 6 | 80 | 480 | 0 | 0 | 480 |  | 480 |
| 5 | Closing |  |  |  |  |  |  |  |  |
| 5.1 | Local Environment Setup | 6 | 80 | 480 | 0 | 0 | 480 | 6000 | 6480 |
| Subtotal |  | 908 |  | 72640 |  |  | 72640 | 11000 | 83640 |
| Reserves (10% Contingency) |  |  |  |  |  |  |  |  | 8364 |
| TOTAL PROJECT COST ESTIMATE |  | 908 |  |  |  |  |  |  | 92004 |

## 2.5 Communications Management Plan

| No. | Stakeholder | Position | Role | Communications Plan |
| --- | --- | --- | --- | --- |
| 1. | Sujina Tuladhar | Project Manager | Leads PM documentation, and sees UC1 and UC4 | Weekly progress meeting, Team members will communicating daily on WhatsApp to share progress, ask questions and coordinate activities. |
| 2. | Pasang Lama | Developer (UC2 and UC5) | Works on the building inventory management and notification modules and keeps the team up to date on work completes and current. | GitHub commits with status note: WhatsApp updates. |
| 3. | Manav Rawal | Developer (UC3 and UC6) | Implements the Browse donations and meal planning features and supports and team with development updates and accomplishment. | Track contribution of code in GitHub and update the team on the status on WhatsApp. |
| 4. | Seetha Letchumi / Ashish Gautam/ Sudeep Lal Bajimaya | Lecturer/ Evaluator | Performs a review of completed deliverables to assure the quality standards are met and make evaluation if needed. | Provides updates to team members through email on submissions, queries or consultation requests relating to the project. |
| 5. | End User( Household testers) | Beneficiary / UAT participant | Gives feedback throughout the testing process to aid in identifying problems and improving the system as a whole. | Collecting feedback from users and feedback forms and demonstrates briefly prior to the submission of the final project. |

## 2.6 Quality Management Plan

| No | Project characteristic/Requirement | Quality Standard | Metric |
| --- | --- | --- | --- |
| 1 | User Registration & Privacy (UC1) | The system should have a secure registration process and two factor authentication (2FA) needs to be reliable and simple to do. | In the test, Email verification needs to be done in a timely manner and the verification emails should be sent out quickly and most of the users should be able to successfully complete the 2FA setup. |
| 2 | Management of Food Inventory (UC2) | Users will need to be able to note down accurate information regarding food items, quantities and expiry dates. | The inventory system should be designed to reduce data entry errors and to properly manage expiration data to ensure that the data stored in the system is accurate. |
| 3 | Browse Food Items and Donations (UC3) | The website should enable visitors to quickly search and filter the food items and donations available on the site. | Search results must be relevant , Filters must work and no donation listings must display errors. |
| 4 | Food Analytics (UC4) | Accurate, readable reports | The amount of calculations and figures in the report should be accurate and reflect the information in the system. |
| 5 | Notification (UC5) | Timely, relevant alerts | Users should be notified about the expiration dates of food and donation opportunities in a timely manner. |
| 6 | Weekly Meal Plan (UC6) | The meal plan feature should be like sensible meal suggestions matched to inventory | Recommendations should use the best ingredients available, but not use items that have passed their expiration date. |
| 7 | Usability (Overall) | The application must be simple and learnable interface | The task should be easy to accomplish and the feature that are important should be no more than 2 clicks to core actions. |
| 8 | Documentation Completeness | Clearly written,Timely presentation of all project management documentations and project assignment requirements. | Documentation should be organized, accurate and complete the final project. |

## 2.7 Risk Management Plan

| No | 1 |
| --- | --- |
| Rank | One |
| Risk Name | Scope Creep |
| Description | There is a possibility that other features can be added on the project that may or may not be the part of project plan. |
| category | Structure/Process (Negative) |
| Risk Response Strategy | Approve all the changes before they are implemented. |
| Probability | High |
| Impact | High |

| No | 2 |
| --- | --- |
| Rank | Two |
| Risk Name | Low Donation Listing Uptake |
| Description | Users have limited space for creating donation listing for testing and demonstration. |
| Category | Market (Negative) |
| Risk Response Strategy | By Developing sample donation information and invite users to participate. |
| Probability | Medium |
| Impact | Medium |

| No | 3 |
| --- | --- |
| Rank | Three |
| Risk Name | Data Privacy Breach |
| Description | The risk that there will be a data privacy breach. User data or food inventory data may be accessible. |
| category | Technological (Negative) |
| Risk Response Strategy | Authentication, secure connections and security checks. |
| Probability | Low |
| Impact | Very High |

| No | 4 |
| --- | --- |
| Rank | Four |
| Risk Name | Team Member Unavailability |
| Description | They may not have a lot of time as they are tacking exam or doing coursework. |
| category | People (Negative) |
| Risk Response Strategy | Record and share responsibilities for work regularly. |
| Probability | Medium |
| Impact | Medium |

| No | 5 |
| --- | --- |
| Rank | Five |
| Risk Name | Budget Overrun |
| Description | Project costs can be over budget estimate |
| category | Financial (Negative) |
| Risk Response Strategy | Keep an eye on costs and deal with problems in a timely manner. |
| Probability | Low |
| Impact | Medium |

| No | 6 |
| --- | --- |
| Rank | six |
| Risk Name | Strong peer/ Lecturer Feedback |
| Description | Useful feedback can enhance the quality and direction of the project. |
| category | Structure/Process (Positive) |
| Risk Response Strategy | Obtain feedback early and use helpful ideas. |
| Probability | Medium |
| Impact | High |

| No | 7 |
| --- | --- |
| Rank | seven |
| Risk Name | Reusable Component Wins |
| Description | Elements that are created for one use case can be reused in multiple other use cases. |
| category | Technological (Positive) |
| Risk Response Strategy | Design reusable components that can be shared across multiple use case to save time and improve work. |
| Probability | Medium |
| Impact | Medium |

| No | 8 |
| --- | --- |
| Rank | Eight |
| Risk Name | Faster than planned delivery |
| Description | The actual development might be done ahead of schedule. |
| category | Financial (Positive) |
| Risk Response Strategy | Make use of additional time for further testing and improvements. |
| Probability | Low |
| Impact | Medium |

## 2.8 Stakeholder Management Strategy

| Stakeholder | Interest | Influence | Quadrant | Management Apporach |
| --- | --- | --- | --- | --- |
| Lecturer (Seetha Letchumi/ Ashish Gautam/ Sudeep Lal Bajimaya) | High | High | Manage Cosely | Submit on time, respond promptly to feedback, clarify requirements early via consultation |
| Project Manager and Teammates | High | High | Manage Closely | Weekly syncs, shared GitHub board, transparent task tracking so no one is blindsided |
| End User (Household tester) | High | Medium | Keep Satisfied | Run a short UAT session, collect feedback, act on the most common complaints. |

# GitHub Link

https://github.com/sujina8/SmartPantry.git

# Reference

- United Nations. (2023). Sustainable development goal 12: Responsible consumption and production. United Nations Department of Economic and Social Affairs. https://sdgs.un.org/goals/goal12

- United Nations. (2023). Sustainable development goal 2: Zero hunger. United Nations Department of Economic and Social Affairs. https://sdgs.un.org/goals/goal2

- Ministry of Agriculture and Food Security Malaysia. (2021). National food security policy action plan 2021–2025. Ministry of Agriculture and Food Security Malaysia. https://www.moa.gov.my