## Sheet1
Cost Estimate
| Project Name: Smart Pantry |  |  | Date:23th June 2026
Prepared By: Sujina Tuladhar, Pasang Lama, Manav Rawal
WBS ID | Work Item / Task | Internal | RM/hour | Internal | External | RM/hour | External | Total | Non-labor | Total
|  | Labor (hrs) |  | RM Total | Labor (hrs) |  | RM Total | Labor RM | RM | Cost RM
1 | Initiating
1.1 | Business Case | 34 | 80 | 2720 | 0 |  | 0 | 2720 |  | 2720
1.2 | Three Sphere Model | 34 | 80 | 2720 | 0 |  | 0 | 2720 |  | 2720
1.3 | Project Charter | 29 | 80 | 2320 | 0 |  | 0 | 2320 |  | 2320
2 | Planning
2.1 | Scope Statement | 17 | 80 | 1360 | 0 |  | 0 | 1360 |  | 1360
2.2 | WorkBreakdown Structure (WBS) | 11 | 80 | 880 | 0 |  | 0 | 880 |  | 880
2.3 | Work Item List | 17 | 80 | 1360 | 0 |  | 0 | 1360 |  | 1360
2.4 | Cost Estimate | 17 | 80 | 1360 | 0 |  | 0 | 1360 |  | 1360
2.5 | Communication Management Plan | 11 | 80 | 880 | 0 |  | 0 | 880 |  | 880
2.6 | Quality Management Plan | 17 | 80 | 1360 | 0 |  | 0 | 1360 |  | 1360
2.7 | Risk Management Plan | 23 | 80 | 1840 | 0 |  | 0 | 1840 |  | 1840
2.8 | Stakeholder Management | 11 | 80 | 880 | 0 |  | 0 | 880 |  | 880
2.9 | Review and Finalize Document | 6 | 80 | 480 | 0 |  | 0 | 480 |  | 480
3 | Executing
3.1 | Analysis and Design | [5 empty] | 0
3.1.1 | Requirements Gathering | 6 | 80 | 480 | 0 |  | 0 | 480 |  | 480
3.1.2 | System Architecture Design | 6 | 80 | 480 | 0 |  | 0 | 480 |  | 480
3.1.3 | Database Scheme design | 11 | 80 | 880 | 0 |  | 0 | 880 |  | 880
3.1.4 | UI/UX Wireframes (Figma) | 11 | 80 | 880 | 0 |  | 0 | 880 | 5000 | 5880
3.2 | Development - Iteration 1
3.2.1 | UC1 User Registration and Privacy | 86 | 80 | 6880 | 0 |  | 0 | 6880 |  | 6880
3.2.2 | UC2 Food Inventory Management | 86 | 80 | 6880 | 0 |  | 0 | 6880 |  | 6880
3.3.3 | UC3 Browse and Claim Donations | 86 | 80 | 6880 | 0 |  | 0 | 6880 |  | 6880
3.3 | Development - Iteration 2
3.3.1 | UC4 Food Analytics Dashboard | 97 | 80 | 7760 | 0 |  | 0 | 7760 |  | 7760
3.3.2 | UC5 Notifications System | 97 | 80 | 7760 | 0 |  | 0 | 7760 |  | 7760
3.3.3 | UC6 Weekly Meal Planner | 97 | 80 | 7760 | 0 |  | 0 | 7760 |  | 7760
3.4 | Testing
3.4.1 | White Box Testing (pytest) | 29 | 80 | 2320 | 0 |  | 0 | 2320 |  | 2320
3.4.2 | Black Box Testing (Selenium) | 17 | 80 | 1360 | 0 |  | 0 | 1360 |  | 1360
3.4.3 | User Acceptance Testing (UAT) | 11 | 80 | 880 | 0 |  | 0 | 880 |  | 880
3.4.4 | Bug Fixing | 29 | 80 | 2320 | 0 |  | 0 | 2320 |  | 2320
4 | Monitoring and Controlling
4.1 | Application Demonstration Preparation | 6 | 80 | 480 | 0 |  | 0 | 480 |  | 480
5 | Closing
5.1 | Local Environment Setup | 6 | 80 | 480 | 0 |  | 0 | 480 | 6000 | 6480
Subtotal |  | 908 |  | 72640 |  |  |  | 72640 | 11000 | 83640
Reserves (10% Contingency) | [9 empty] | 8364
TOTAL PROJECT COST ESTIMATE |  | 908 | [7 empty] | 92004
ASSUMPTIONS
1. Internal labor rate = RM 80/hr (industry standard for junior web developer in Malaysia).
2. No external labor - all development by Sujina Tuladhar, Pasang Lama, and Manav Rawal.
3. Total estimated internal hours = 908 hrs.
4. Non-labor: UI/UX design (RM 5,000), AWS EC2 hosting setup (RM 6,000).
5. 10% contingency reserve for unexpected costs.
6. All dev tools (Django, React, PostgreSQL, GitHub, GanttProject) are free/open-source.
7. Hardware already owned by team - no additional hardware cost.
Weekly Cost Breakdown
| WBS Activity | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Total Hrs | Cost (RM)
| 1. Initiating (Business Case, Three Sphere Model, Charter) | Wk1: 40; Wk2: 40; Wk3: 17 | 97 | 7760
| 2. Planning (Scope, WBS, Work Items, Cost Estimate, Mgmt Plans) | Wk2: 23; Wk3: 40; Wk4: 40; Wk5: 28 | 130 | 10400
| 3.1 Requirements Gathering | Wk5: 6 | 6 | 480
| 3.2 System Architecture Design | Wk5: 6 | 6 | 480
| 3.3 Database Schema Design | Wk6: 11 | 11 | 880
| 3.4 UI/UX Wireframes (Figma) | Wk6: 11 | 11 | 880
| 4.1 UC1 User Registration and Privacy | Wk6: 17; Wk7: 40; Wk8: 29 | 86 | 6880
| 4.2 UC2 Food Inventory Management | Wk6: 17; Wk7: 40; Wk8: 29 | 86 | 6880
| 4.3 UC3 Browse and Claim Donations | Wk6: 17; Wk7: 40; Wk8: 29 | 86 | 6880
| 5.1 UC4 Food Analytics Dashboard | Wk8: 11; Wk9: 40; Wk10: 40; Wk11: 6 | 97 | 7760
| 5.2 UC5 Notifications System | Wk8: 11; Wk9: 40; Wk10: 40; Wk11: 6 | 97 | 7760
| 5.3 UC6 Weekly Meal Planner | Wk8: 11; Wk9: 40; Wk10: 40; Wk11: 6 | 97 | 7760
| 6.1 White Box Testing (pytest) | Wk11: 29 | 29 | 2320
| 6.2 Black Box Testing (Selenium) | Wk11: 6; Wk12: 11 | 17 | 1360
| 6.3 User Acceptance Testing (UAT) | Wk12: 11 | 11 | 880
| 6.4 Bug Fixing | Wk12: 17; Wk13: 12 | 29 | 2320
| 7.1 Local Environment Setup | Wk14: 6 | 6 | 480
| 7.2 Application Demonstration Preparation | Wk14: 6 | 6 | 480
| Total Hours / Week | 40 | 40 | 40 | 40 | 40 | 40 | 74 | 120 | 120 | 120 | 120 | 52 | 40 | 24 | 908 | 72640
| Cost / Week (RM) | 3195 | 3195 | 3178 | 3165 | 3165 | 3221 | 5888 | 9632 | 9619 | 9586 | 9586 | 4143 | 3179 | 1888